## Tabelle1
Date | Task | TODO
2023-08-06 | pdf to text | compare performance using different stemmer (algorthmic vs. Dictionary)
| database: elasticsearch | tutorial: https://radimrehurek.com/gensim/auto_examples/
| tokenizing, stemming, stoplist | research: LDA
| Docker | research: BERTopic
2023-08-07 | research | PROBLEM: Elasticsearch max. dimension of dense vector is 2048, vocab size of corpus is bigger (7243), SOLUTION: create multple features/ properties for large vector and search multiple times when querying OR use PCA/ AE to reduce dimensionality
| improved structure and consistency in elasticsearch file | Usage Sentence embeddings rather than word embeddings? Ann. Beschreiben
2023-08-08 | research
2023-08-09 | research, argparse input file/dir | Google's universal Sentence Encoder: Alter shapes to fix problem (HOW?), InferSent has same difference problem
2023-08-10 | (slurm) sbatch skript für Visualisierung, Alias in ~/.zshrc für kopieren von remote cluster.ies zu local dir, dir: visualization & error_logs im home, requirements.txt für simple venv Erstellung, argparse output dir | Add pipeline image for different models, which shows if stopwords were removed by me or model etc. to bachelor thesis
2023-08-11 | Matrix aus Bildern (vgl. CIFAR-10), lokale Database mit mehr PDFs füllen | analysis/ evaluation ideas cf. Notability 23.08.2023
2023-08-12 | pdf2image auf Cluster, visualized 9 most similar images for sample query as matrix | why are cluster sizes of PCA results imbalanced? Because they are too sparse
2023-08-13 | tfidf: document term matrix, cosine similarity, tfidf vectorization of ocument corpus, google's universal-sentence-encoder | Cluster: bewerten lassen
2023-08-14 | infer pretrained sentence encoder without db, bc embedding is too big for maximum dense vector size | Cluster für Bilder und Text nutzbar
2023-08-15 | huggingface: init, save, load sentence transformer, added as embedding to elasticSearch db | Universal Sentence Encoder: nicht auf GPU, finde Artikel mit gleichem Problem online
bis 22.08.2023 | Urlaub
2023-08-23 | read Universal Encoder paper, log path != result path (sbatch skripts on cluster),
2023-08-24 | multiple tfidf vectors for different tasks (1. similarity between documents omitting words which occur only once in the corpus, 2. finding specific documents omitting words which occur in every document, etc.) -> reduce vector size (=#unique words), BA: assumption is that there are similarities (content wise and in terms of visual appearance) between documents of same type (eg. Urkunde) | Eigenfaces: hohe dim <-> sparse <-> Clustern schwer
2023-08-25 | InferSent hypothese: project does not support training: https://github.com/facebookresearch/InferSent/issues/82 , Universal Sentence Encoder: the embedding uses n-grams of documents close to current doc (like a window) to embed it, cf. DAN in https://amitness.com/2020/06/universal-sentence-encoder/ -> unable to fix subtraction problem, started working on eigenfaces
2023-08-26 | cluster PCA results of images | Why are residual graph so similar for both latent dimensions?
2023-08-29 | solved errors of PCA clustering, added PCA-Cluster to database, DB has to be deleted to update index (!!!), deleted one tfidf embedding since it is too big, other tfidf is null vector (Problem!), db is searchable for same cluster documents
2023-08-30 | AutoEncoder + Kmeans Clustering | BA: Pipeline Bild s. Christians Zeichnung, 62GB Daten -> offline verarbeiten -> DB -> auf kleinem System durchsuchbar
2023-08-30 | TFIDF: strip accents in db embedding, created preprocessing class which can be used instead of default preprocessor | BA: AE latent space normal verteilt????
2023-08-31 | added TFIDF all-zero-flag, restructured repo: run everything from main.py now
2023-09-01 | InferSent: + encoder layer of AE to reduce dimensionality in db & query (bad results) possible, compared (interactively) Cluster Algos: DBSCAN (nicht parametrisch != Kmeans), HDBSCAN (nicht parametrisch != Kmeans), OPTICS (nicht parametrisch != Kmeans), KMeans
2023-09-02 | Eigenfaces: 3-4 components, visualize via 3d scatter plot (matplotlib)/ 4d via colors, Eigenfaces: display Entwicklung von Rekonstruktionsfehler: way to find best # components, added Cluster Algo: Variationale Baysian Mixture Model after PCA, try AE with higher dimensionality and use PCA to visualize, tried Convolutional AE: https://blog.keras.io/building-autoencoders-in-keras.html, compared clustering algos on tfidf embedding, added comparison of exmaple images per cluster per algo, Universal Sentence Encoder: huggingface version also uses tensoflow (fork) cf. https://huggingface.co/Dimitre/universal-sentence-encoder & https://huggingface.co/vprelovac/universal-sentence-encoder-4 | BA: Kmeans Hypothese ist, dass Daten normalverteilt. Deshalb Kmeans cluster eher rund -> deshalb wäre anderer Algo, z.B. Var. Bayesian Mixture Model interessant
2023-09-04 | Annoy: similar documents to certain one local, little information online https://www.slideshare.net/erikbern/approximate-nearest-neighbor-methods-and-vector-models-nyc-ml-meetup and https://github.com/spotify/annoy ; FastSent: import fails
2023-09-05 | used WordClouds, LDA and BERTopic on sample query results, UI version 1.0, Betreuer Treffen Uni | Lizenzen: GPL kann man nicht so einfach nutzen
2023-09-05 | cluster query results displayed in UI | Conv. AE is bad
2023-09-06 | TfidfPreprocessor: deleted unused Code (fit_transform und fit) | Cli: Subprocesss, which display flags per key program name
2023-09-07 | multiple query results displayable in UI | main.py: dict instead of if else
2023-09-08 | models saved to disk, db init from disk
11-12.09.2023 | Dienstreise | find a way to save all precomputed similarity values space efficient -> offline computation; Adjazenzmatrix? Value & docs (d1,d2)=x12
2023-09-12 | UI Version 2
2023-09-13 | added Wordcloud for one document to UI V2, VSCode on cluster | BA: # Docs = 866.000
2023-09-14 | added Wordcloud for multiple documents to UI V2
2023-09-15 | fuzzy full-text search, DB: Elasticsearch | Clustering after PCA: Cluster on PCA data, not original one!
2023-09-16 | id are hashes of text, only add new docs | later/ all data: use subset of ca. 50.000 documents to train Eigenfaces
2023-09-17 | BA: Clustering | BA: Online/ Offline (memory) -> Ausblick: PNGs mit AE/ CNN
2023-09-18 | OPTICS: reachability plot + clustering | BERTopic: omit stopwords
2023-09-19 | OPTICS: on 32x32 and on PCA version (PCA/eigendoc is better), PCA on 2^2, 5^2, 14^2 -> 2^2 is best, eigendocs code und BA: eigendocs, pdf2png only new docs | Topic Analysis: Offline -> BERTopic to get topics, Online: Wordclouds on Cluster
2023-09-20 | hash: of bytes of file, # PCA components from cumulative explained variance knee/ or reconstrcution error (4-20 total), 32x32 -> PCA -> OPTICS, Init_db: multiprocessing
2023-09-21 | work event | reduce tfidf vocab : SVD/ https://stackoverflow.com/questions/61274499/reduce-dimension-of-word-vectors-from-tfidfvectorizer-countvectorizer , https://scikit-learn.org/stable/auto_examples/text/plot_document_clustering.html LSA !!!!
2023-09-22 | cluster: argmax(pca weights), clustering on 13 instead of 2dims, BA: related work section 3, 2=fundamentals/state of the art, etc. cf. 20.09.2023 Vortrag, BA: SVD gibt Bausteine, mittelwert automatisch in Implementierung, aber wichtig in Text
2023-09-23 | termfrequency | OPTICS: threshold hierarchical clustering, reduce threshold and observe new documents -> schwer
2023-09-24 | BA: soft cosine similarity
2023-09-25 | Urlaub | database on cluster
2023-09-26 | insert only certain embeddings into db, BA: term frequency, (soft) cosine sim.
2023-09-27 | RSME usage for PCA reconstruction error, time per embedding, fix AE dimension, argmax cluster on white canvas input, BA: tokenization etc. | BA: max_h, max_b eigendocs preprocessing Infos of relative dimension
2023-09-28 | BA: TFIDF, Doc2Vec | Eigenfaces dim = Data type (image higher than doc)?
2023-09-29 | restructured init_db (omitted some inefficiency), BA: tfidf implementation | PCA: padded vectors -> encodes sizes of originals
BA: pro section: first problem, then how to solve it, then techniques used
AE: 0% reconstruction error
BA: high level eval of image clustering etc.
BA: qualitativ für 195 docs eval (Vorstellung vs Realität, welche Merkmale fallen auf?)
besten Algo auf labeled doc clustering Datensatz finden
Eval: Metrik für Cluster finden
Eval: semantic vs layout basiert Verfahren (vgl)