## Tabelle1
Date | Task | TODO
2023-08-06 | pdf to text | compare performance using different stemmer (algorthmic vs. Dictionary)
| database: elasticsearch | tutorial: https://radimrehurek.com/gensim/auto_examples/
| tokenizing, stemming, stoplist | research: LDA
| Docker | research: BERTopic
2023-08-07 | research | PROBLEM: Elasticsearch max. dimension of dense vector is 2048, vocab size of corpus is bigger (7243), SOLUTION: create multple features/ properties for large vector and search multiple times when querying OR use PCA/ AE to reduce dimensionality
| improved structure and consistency in elasticsearch file | Usage Sentence embeddings rather than word embeddings? Ann. Beschreiben
2023-08-08 | research | CNN Ähnlichkeiten auf images der PDFs erkennen lassen
2023-08-09 | research, argparse input file/dir | Google's universal Sentence Encoder: Alter shapes to fix problem (HOW?)
2023-08-10 | (slurm) sbatch skript für Visualisierung, Alias in ~/.zshrc für kopieren von remote cluster.ies zu local dir, dir: visualization & error_logs im home, requirements.txt für simple venv Erstellung, argparse output dir | Compare .png of documents using either 1. AE, 2. Eigenface/-phase (cf. PCA), 3. from paper
2023-08-11 | Matrix aus Bildern (vgl. CIFAR-10), lokale Database mit mehr PDFs füllen | Add pipeline image for different models, which shows if stopwords were removed by me or model etc. to bachelor thesis
2023-08-12 | pdf2image auf Cluster, visualized 9 most similar images for sample query as matrix | analysis/ evaluation ideas cf. Notability 23.08.2023
2023-08-13 | tfidf: document term matrix, cosine similarity, tfidf vectorization of ocument corpus, google's universal-sentence-encoder | why are cluster sizes of PCA results imbalanced? Because they are too sparse
2023-08-14 | infer pretrained sentence encoder without db, bc embedding is too big for maximum dense vector size
2023-08-15 | huggingface: init, save, load sentence transformer, added as embedding to elasticSearch db | TFIDF: automatic preprocessing? Ggf. stemming/ lemmatization (using NLTK) to reduce vocabulary
bis 22.08.2023 | Urlaub | TFIDF: preprocessing: diskretisiere Zahlen: ersetze bis fünfstellig z.B. durch small_number etc.
2023-08-23 | read Universal Encoder paper, log path != result path (sbatch skripts on cluster), | TFIDF: add extra cell to embedding, acts as flag for null embeddings
2023-08-24 | multiple tfidf vectors for different tasks (1. similarity between documents omitting words which occur only once in the corpus, 2. finding specific documents omitting words which occur in every document, etc.) -> reduce vector size (=#unique words), BA: assumption is that there are similarities (content wise and in terms of visual appearance) between documents of same type (eg. Urkunde) | InferSent: + encoder layer of AE to reduce dimensionality
2023-08-25 | InferSent hypothese: project does not support training: https://github.com/facebookresearch/InferSent/issues/82 , Universal Sentence Encoder: the embedding uses n-grams of documents close to current doc (like a window) to embed it, cf. DAN in https://amitness.com/2020/06/universal-sentence-encoder/ -> unable to fix subtraction problem, started working on eigenfaces | Cluster Algo: DBSCAN (nicht parametrisch != Kmeans)
2023-08-26 | cluster PCA results of images | Cluster Algo: HDBSCAN (nicht parametrisch != Kmeans)
2023-08-29 | solved errors of PCA clustering, added PCA-Cluster to database, DB has to be deleted to update index (!!!), deleted one tfidf embedding since it is too big, other tfidf is null vector (Problem!), db is searchable for same cluster documents | Cluster Algo: OPTICS (nicht parametrisch != Kmeans)
2023-08-30 | AutoEncoder + Kmeans Clustering | Cluster: bewerten lassen
2023-08-30 | TFIDF: strip accents in db embedding | Cluster für Bilder und Text nutzbar
Universal Sentence Encoder: nicht auf GPU, finde Artikel mit gleichem Problem online
Universal Sentence Encoder: try huggingface version
Eigenfaces: find paper
Eigenfaces: hohe dim <-> sparse <-> Clustern schwer
Eigenfaces: 3-4 components, visualize via 3d scatter plot (matplotlib)/ 4d via colors
Eigenfaces: display Entwicklung von Rekonstruktionsfehler, way to find best # components
Cluster Algo: Variationale Baysian Mixture Model after PCA
BA: Pipeline Bild s. Christians Zeichnung, 62GB Daten -> offline verarbeiten -> DB -> auf kleinem System durchsuchbar
BA: AE latent space normal verteilt????
try Convolutional AE
try AE with higher dimensionality and use PCA to visualize
BA: Kmeans Hypothese ist, dass Daten normalverteilt. Deshalb Kmeans cluster eher rund -> deshalb wäre anderer Algo, z.B. Var. Bayesian Mixture Model interessant
BA: OPTICS etc. in Absatz Funktion erklären + Referenz
Lizenzen: GPL kann man nicht so einfach nutzen